NeoSkill.uz

Decision & Risk Register

Product qarorlari, ochiq savollar va risk nazorati

| Holat | Working baseline |
| --- | --- |
| Versiya | 1.1 |
| Sana | 7-sentabr, 2026 |
| Asos | UPDATE NeoSkill TZ v1.1 |

# 1. Decision Register

Status meaning — ACCEPTED = ishlash uchun baseline. PROPOSED = Codex bu qarorni product rule sifatida qabul qilmasin; PO tasdiqlamaguncha chetlab o‘tsin.

| ID | Mavzu | Qaror | Status | Manba |
| --- | --- | --- | --- | --- |
| D-001 | MVP payment | Manual paid Enrollment Request; Click/Payme OUT. | ACCEPTED | TZ v1.1 |
| D-002 | Free enrollment | Free course → ACTIVE auto-enrollment; no admin approval. | ACCEPTED | TZ v1.1 |
| D-003 | Lesson completion | “Darsni tugatdim” persisted state unlockning basisidir. | ACCEPTED | TZ v1.1 |
| D-004 | Practice | Simple text/example/link + completed flag; no file grading. | ACCEPTED | TZ v1.1 |
| D-005 | Video | Managed URL/stream integration; upload/transcoding pipeline shart emas. | ACCEPTED | TZ v1.1 |
| D-006 | Ratings | User rating/review MVPda yo‘q; admin testimonials. | ACCEPTED | TZ v1.1 |
| D-007 | Language selector | Faqat real translated content bo‘lsa ko‘rsatiladi. | ACCEPTED | TZ v1.1 |
| D-008 | Frontend | Next.js + TypeScript + Tailwind. | ACCEPTED | TZ recommendation |
| D-009 | Backend | NestJS tanlash: end-to-end TypeScript va Codex context simplicity uchun. | PROPOSED | PM recommendation |
| D-010 | Database | PostgreSQL; Redis MVPda yo‘q. | ACCEPTED | TZ v1.1 |
| D-011 | Auth transport | HTTP-only cookie based session/JWT approach. | PROPOSED | TZ recommendation |
| D-012 | Telegram field | Phone required; Telegram username optional. | PROPOSED | PM default |
| D-013 | Test answer reveal | MVPda correct-answer review majburiy emas. | PROPOSED | TZ allows later setting |
| D-014 | Certificate | Phase 2. | PROPOSED | PM scope control |
| D-015 | Course access expiry | MVPda expiry yo‘q. | PROPOSED | PM default |

# 2. Risk Register

| ID | Risk | Impact | Likelihood | Ta’rif | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Scope creep | High | High | Payment/chat/AI/app kabi funksiyalar MVPga kirib ketishi. | Non-goals + change request gate. | PO |
| R-02 | Access control bug | High | Medium | Paid content unauthorized userga ochilishi. | Server-side guard + IDOR regression. | Tech/QA |
| R-03 | Progress inconsistency | High | Medium | Dashboard va course progress turlicha hisoblanishi. | Bitta canonical progress formula/service. | Tech |
| R-04 | Unlock edge cases | High | Medium | Retry/pass/final topic logikasi buzilishi. | Unit/integration tests + UAT-09..13. | Tech/QA |
| R-05 | Admin complexity | Medium | Medium | CRUDlar admin uchun chalkash bo‘lishi. | Simple hierarchy UI + validation + preview. | PO/UX |
| R-06 | Video reliability | Medium | Medium | External URL ishlamasligi/provider cheklovi. | Provider abstraction + invalid URL handling. | Tech |
| R-07 | Manual sales operations | Medium | High | Request ko‘payganda approve queue sekinlashadi. | Pending count/filter; Phase 2 payment trigger. | Ops/PO |
| R-08 | Codex large-change drift | High | High | Bir prompt juda ko‘p file/business ruleni buzishi. | One task ID per change; test/review gate. | PM |
| R-09 | Untracked decisions | Medium | High | Code product qaroridan oldinga ketadi. | DECISIONS.md mandatory update. | PO/PM |
| R-10 | No real content during QA | Medium | Medium | UI fake data bilan yaxshi, real hierarchyda buziladi. | Realistic seed: free + paid course. | PM/QA |

# 3. Change Request qoidasi

Yangi feature/g‘oya nomi va muammo yoziladi.

U MVP core flowga blocker yoki release necessity ekanligi baholanadi.

Existing storyga ta’siri, data model va dependency aniqlanadi.

PO qarori: MVP / Phase 2 / Reject.

MVPga kirsa yangi Story ID va acceptance criteria yoziladi; Decision Register update qilinadi.

Shundan keyingina Codexga implementation task beriladi.

# 4. PO approval queue

| Savol | Default | PO qarori |
| --- | --- | --- |
| NestJS backendni baseline qilamizmi? | Ha — tavsiya. | ____ |
| Telegram username optionalmi? | Ha. | ____ |
| Testdan keyin correct answers ko‘rsatiladimi? | Yo‘q, MVP. | ____ |
| Course access expiry bormi? | Yo‘q, MVP. | ____ |
| Certificate Phase 2mi? | Ha. | ____ |

# UPDATE v1.1 - Design decisions

| ID | Decision | Status | Source |
| --- | --- | --- | --- |
| D-016 | Figma NeoSkill MVP uchun visual source of truth. | ACCEPTED | PO instruction, 7-sentabr 2026 |
| D-017 | TZ/PRD/Decisions product behavior uchun Figma’dan ustun. Figma’dagi functional kamchilik ko‘chirilmaydi. | ACCEPTED | PO instruction |
| D-018 | Exact design token qiymatlari Figma’dan olinadi; Codex guessed brand HEX/spacing bilan final UI qilmaydi. | ACCEPTED | Design implementation rule |
| D-019 | Figma’da out-of-scope element ko‘rinsa, style saqlanib product CTA/flow MVP qoidalariga moslanadi. | ACCEPTED | MVP scope control |

## Design risklari

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Figma barcha state/frame’larni bermaydi | UI incomplete yoki inconsistent bo‘lishi mumkin | Missing states DESIGN_SYSTEM qoidasi bo‘yicha mavjud visual til ichida yaratiladi. |
| Codex Figma qiymatlarini taxmin qiladi | Brand drift | NS-004 token audit P0; guessed exact values taqiqlanadi. |
| Figma product scope bilan zid | Dead/fake feature paydo bo‘ladi | PRD/Decisions behavior precedence; deviation log. |
| Pixel matching accessibilityni buzadi | Usability regressiya | Focus/semantic/contrast quality gate designni xavfsiz tarzda to‘ldiradi. |